## Sheet1
Sample Risk Management Register for Project XXXX
Risk Identification |  |  | Qualitative Risk Assessment | [8 empty] | Risk Response Plan |  | Monitoring and Control
# | Category | Risk Description | Probability | Impact | Risk Matrix | [6 empty] | Response Strategy | Response Actions | Responsibile Entity | Status: Date and Review Comments
1 | Ethical | Missing Algorithm Ethics Checks | H | H | Probability | VH | [5 empty] | Ensure the developed algorithm is inspected by AI Ethics Council to make a conscious and transparent decision regarding the use of the model for the use case at hand | 1. Schedule regular meetings with AI Ethics Council | Data Scientist Team Lead
|  | Missing/incomplete data ethics checks can degrade the integrity of the model, rendering it unusable for making predictions. |  |  |  | H |  |  |  | X
M
L
VL
[7 empty] | VL | L | M | H | VH
Impact
2 | Legal | Loss/Disclosure of Sensitive Information | M | VH | Probability | VH | [5 empty] | Ensure contracts are written to prevent the vendor from collecting/sharing agency data. | 1. Schedule meeting with Acquisition and Chief Privacy Officer | Cybersecurity Lead
|  | Use of AI SaaS inadvertently leaks sensitive information (including PII) to the vendor and is published or integrated into their AI system. |  |  |  | H
[6 empty] | M |  |  |  |  | X
L
VL
[7 empty] | VL | L | M | H | VH
Impact
3 | Technical | No Adequate Backup Systems and Fallback Plans | H | H | Probability | VH | [5 empty] | Schedule frequent backups to prevent loss of data | 1. Setup backup plan | Network Engineering Lead
|  | AI systems need to be resilient and secure |  |  |  | H |  |  |  | X |  |  | 2. Document backup/archive policy
M
L
VL
[7 empty] | VL | L | M | H | VH
Impact
4 | Ethical | Algorithmic Bias Risk | H | H | Probability | VH | [5 empty] | Implement data balancing techniques and regularly audit model outputs for fairness. | 1. Develop mitigation plan | Data Scientist Team Lead
|  | Potential bias in AI model predictions due to imbalanced training data. |  |  |  | H |  |  |  | X
M
L
VL
[7 empty] | VL | L | M | H | VH